## Time harmonogram
Time harmonogram
Supplier:
| Number | Název (name of activity) | Beginning of activity | End of activity | Price (CZK) | Nh | Počet prac. dní | Prům. počet prac. | October 2007 |  |  |  | November 2007 |  |  |  | December 2007 |  |  |  | January 2008 |  |  |  | February 2008 |  |  |  | March 2008
[9 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| 0001 | Rekonstruction of building into production hall | 2007-10-01 | 2008-03-31 | 9938584.42 | 9123.13 | 130 | 5
2
| 1 | Zmení práce (Earthworks) | 2007-10-05 | 2007-10-20 | 111377.03 | 173.89 | 11 | 1.86
3
| 2 | Základy a zvláštní zakládání (Foundations) | 2007-10-17 | 2007-10-31 | 268845.78 | 327.41 | 11 | 3.5
3
| 3 | Svislé a kompletní konstrukce (Vertical constructions) | 2007-10-29 | 2007-11-14 | 406860.56 | 352.35 | 13 | 3.19
3
| 4 | Vodorovné konstrukce (Horizontal constructions) | 2007-11-12 | 2007-11-20 | 22671.26 | 40.4 | 7 | 0.68
3
| 5 | Komunikace (Roads) | 2008-01-21 | 2008-02-20 | 176925.14 | 88.44 | 23 | 0.45
3
| 61 | Upravy povrchů vnitřní (Construction of surfaces - internal) | 2007-12-18 | 2008-01-19 | 952704.08 | 1340.88 | 23 | 6.86
3
| 62 | Úpravy povrchů vnější (Construction of surfaces - external) | 2008-02-26 | 2008-03-25 | 887663.81 | 566.83 | 20 | 3.33
3
| 63 | Podlahy a podlahové konstrukce (Floors and floor constructions) | 2008-01-22 | 2008-02-16 | 819513.53 | 835.73 | 18 | 5.46
3
| 64 | Výplně otvorů (Opening panels) | 2007-11-11 | 2007-11-21 | 26479.2 | 38.57 | 9 | 0.5
3
| 8 | Trubní vedení (Pipage, conduction) | 2007-12-10 | 2007-12-24 | 263702.44 | 203.61 | 11 | 2.18
3
| 9 | Ostatní konstrukce, bourání (Other constructions, demolition works) | 2007-10-02 | 2007-10-17 | 163360 | 0 | 12 | 0
3
| 94 | Lešení a stavební výtahy (Scaffolding, building lifts) | 2007-10-01 | 2008-03-31 | 208747.5 | 379.86 | 130 | 0.34
3
| 95 | Dokončovací konstrukce (Finishing construcructions) | 2007-11-28 | 2007-12-18 | 5371.15 | 20.19 | 15 | 0.16
3
| 96 | Bourání konstrukcí (Demolition of constructions) | 2007-10-12 | 2007-10-28 | 11915.63 | 33.84 | 12 | 0.33
3
| 97 | Prorážení otvorů (Tapping) | 2007-10-22 | 2007-11-11 | 152593.11 | 674.1 | 15 | 5.29
3
| 98 | Demolice (Demolition) | 2007-11-07 | 2007-11-17 | 44691.78 | 127.69 | 7 | 2.15
3
| 99 | Staveništní přesun hmot (Building site material moving) | 2007-10-01 | 2008-03-31 | 240742.73 | 998.12 | 130 | 0.9
3
| F0862 | Požární zabezpečení = EPS (Fire protection) | 2008-02-25 | 2008-03-16 | 249000 | 0 | 14 | 0
3
| F0863 | Zabezpečovací zařízení (Protection device) | 2008-02-11 | 2008-03-02 | 112000 | 0 | 14 | 0
3
| F1015 | Doplňkové stavby (Additional buildings) | 2008-01-26 | 2008-02-09 | 738335 | 0 | 11 | 0
3
| 711 | Izolace proti vodě (Waterproofing) | 2007-11-23 | 2007-12-05 | 592242.83 | 355.28 | 10 | 4.18
3
| 713 | Izolace tepelné (Thermal insulation) | 2007-12-03 | 2007-12-15 | 7602.75 | 6.01 | 9 | 0.08
3
| 722 | Vnitřní vodovod (Internal water tap) | 2007-12-19 | 2008-01-16 | 99708.27 | 66.48 | 21 | 0.37
3
| 766 | Konstrukce truhlářské (Joinery constructions) | 2008-03-06 | 2008-03-23 | 165578.56 | 21.4 | 12 | 0.21
3
| 767 | Konstrukce zámečnické (Locksmith constructions) | 2008-01-26 | 2008-02-11 | 290497.36 | 107.71 | 13 | 0.97
3
| 771 | Podlahy z dlaždic a obklady (Floors from tiles, wall facing) | 2008-02-12 | 2008-03-11 | 997088.34 | 1264.44 | 20 | 7.44
3
| 776 | Podlahy povlakové (Coating floors) | 2008-03-10 | 2008-03-27 | 19325.63 | 13.35 | 14 | 0.11
3
| 777 | Podlahy ze syntetických hmot (Synthetic floors) | 2008-03-03 | 2008-03-13 | 22883.2 | 49.07 | 9 | 0.64
3
| 781 | Obklady keramické (Ceramic facing) | 2008-02-02 | 2008-02-18 | 8644.55 | 13.78 | 13 | 0.12
3
| 783 | Nátěry (Coating) | 2008-03-08 | 2008-03-20 | 38216.12 | 1.82 | 10 | 0.02
3
| 784 | Malby (Paintings) | 2008-03-16 | 2008-03-31 | 150457.85 | 372.25 | 12 | 3.65
3
| M21 | Elektromontáže (Electro assembly works) | 2007-12-14 | 2008-03-13 | 1080852 | 0 | 65 | 0
3
| D96 | Přesuny suti a vybouraných hmot (Shifts of rubble) | 2007-11-20 | 2007-12-18 | 194696.07 | 649.64 | 21 | 3.64
3
| 3 VRN | Přesun stavebních kapacit (moving of construction capacities) | 2007-10-01 | 2008-03-31 | 169008.83 | 0 | 130 | 0
3
| 5 VRN | Zařízení staveniště (building site accesories) | 2007-10-01 | 2008-03-31 | 238282.33 | 0 | 130 | 0
3

## Financial plan - budget
Financial plan (budget) of building
Supplier:
Number | Název (name of activity) | Beginning of activity | End of activity | Price (CZK) | Nh | Počet prac. dní | Prům. počet prac. | October 2007 |  |  |  | November 2007 |  |  |  | December 2007 |  |  |  | January 2008 |  |  |  | February 2008 |  |  |  | March 2008
[8 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
0001 | Rekonstruction of building into production hall | 2007-10-01 | 2008-03-31 | 9938584.42 | 9123.13 | 130 | 5
1 | Zmení práce (Earthworks) | 2007-10-05 | 2007-10-20 | 111377.03 | 173.89 | 11 | 1.86
2 | Základy a zvláštní zakládání (Foundations) | 2007-10-17 | 2007-10-31 | 268845.78 | 327.41 | 11 | 3.5
3 | Svislé a kompletní konstrukce (Vertical constructions) | 2007-10-29 | 2007-11-14 | 406860.56 | 352.35 | 13 | 3.19
4 | Vodorovné konstrukce (Horizontal constructions) | 2007-11-12 | 2007-11-20 | 22671.26 | 40.4 | 7 | 0.68
5 | Komunikace (Roads) | 2008-01-21 | 2008-02-20 | 176925.14 | 88.44 | 23 | 0.45
61 | Upravy povrchů vnitřní (Construction of surfaces - internal) | 2007-12-18 | 2008-01-19 | 952704.08 | 1340.88 | 23 | 6.86
62 | Úpravy povrchů vnější (Construction of surfaces - external) | 2008-02-26 | 2008-03-25 | 887663.81 | 566.83 | 20 | 3.33
63 | Podlahy a podlahové konstrukce (Floors and floor constructions) | 2008-01-22 | 2008-02-16 | 819513.53 | 835.73 | 18 | 5.46
64 | Výplně otvorů (Opening panels) | 2007-11-11 | 2007-11-21 | 26479.2 | 38.57 | 9 | 0.5
8 | Trubní vedení (Pipage, conduction) | 2007-12-10 | 2007-12-24 | 263702.44 | 203.61 | 11 | 2.18
9 | Ostatní konstrukce, bourání (Other constructions, demolition works) | 2007-10-02 | 2007-10-17 | 163360 | 0 | 12 | 0
94 | Lešení a stavební výtahy (Scaffolding, building lifts) | 2007-10-01 | 2008-03-31 | 208747.5 | 379.86 | 130 | 0.34
95 | Dokončovací konstrukce (Finishing construcructions) | 2007-11-28 | 2007-12-18 | 5371.15 | 20.19 | 15 | 0.16
96 | Bourání konstrukcí (Demolition of constructions) | 2007-10-12 | 2007-10-28 | 11915.63 | 33.84 | 12 | 0.33
97 | Prorážení otvorů (Tapping) | 2007-10-22 | 2007-11-11 | 152593.11 | 674.1 | 15 | 5.29
98 | Demolice (Demolition) | 2007-11-07 | 2007-11-17 | 44691.78 | 127.69 | 7 | 2.15
99 | Staveništní přesun hmot (Building site material moving) | 2007-10-01 | 2008-03-31 | 240742.73 | 998.12 | 130 | 0.9
F0862 | Požární zabezpečení = EPS (Fire protection) | 2008-02-25 | 2008-03-16 | 249000 | 0 | 14 | 0
F0863 | Zabezpečovací zařízení (Protection device) | 2008-02-11 | 2008-03-02 | 112000 | 0 | 14 | 0
F1015 | Doplňkové stavby (Additional buildings) | 2008-01-26 | 2008-02-09 | 738335 | 0 | 11 | 0
711 | Izolace proti vodě (Waterproofing) | 2007-11-23 | 2007-12-05 | 592242.83 | 355.28 | 10 | 4.18
713 | Izolace tepelné (Thermal insulation) | 2007-12-03 | 2007-12-15 | 7602.75 | 6.01 | 9 | 0.08
722 | Vnitřní vodovod (Internal water tap) | 2007-12-19 | 2008-01-16 | 99708.27 | 66.48 | 21 | 0.37
766 | Konstrukce truhlářské (Joinery constructions) | 2008-03-06 | 2008-03-23 | 165578.56 | 21.4 | 12 | 0.21
767 | Konstrukce zámečnické (Locksmith constructions) | 2008-01-26 | 2008-02-11 | 290497.36 | 107.71 | 13 | 0.97
771 | Podlahy z dlaždic a obklady (Floors from tiles, wall facing) | 2008-02-12 | 2008-03-11 | 997088.34 | 1264.44 | 20 | 7.44
776 | Podlahy povlakové (Coating floors) | 2008-03-10 | 2008-03-27 | 19325.63 | 13.35 | 14 | 0.11
777 | Podlahy ze syntetických hmot (Synthetic floors) | 2008-03-03 | 2008-03-13 | 22883.2 | 49.07 | 9 | 0.64
781 | Obklady keramické (Ceramic facing) | 2008-02-02 | 2008-02-18 | 8644.55 | 13.78 | 13 | 0.12
783 | Nátěry (Coating) | 2008-03-08 | 2008-03-20 | 38216.12 | 1.82 | 10 | 0.02
784 | Malby (Paintings) | 2008-03-16 | 2008-03-31 | 150457.85 | 372.25 | 12 | 3.65
M21 | Elektromontáže (Electro assembly works) | 2007-12-14 | 2008-03-13 | 1080852 | 0 | 65 | 0
D96 | Přesuny suti a vybouraných hmot (Shifts of rubble) | 2007-11-20 | 2007-12-18 | 194696.07 | 649.64 | 21 | 3.64
3 VRN | Přesun stavebních kapacit (moving of construction capacities) | 2007-10-01 | 2008-03-31 | 169008.83 | 0 | 130 | 0
5 VRN | Zařízení staveniště (building site accesories) | 2007-10-01 | 2008-03-31 | 238282.33 | 0 | 130 | 0
Cena za týden (Price for a week)
Cena za měsíc (Price for a month)
Cena za čtvrtletí (Price for a quarter)
Cena za rok (Price for a year)

## Financial plan - accounting
Financial plan (accounting) of building
Supplier:
Number | Název (name of activity) | Beginning of activity | End of activity | Price (CZK) | Nh | Počet prac. dní | Prům. počet prac. | October 2007 |  |  |  | November 2007 |  |  |  | December 2007 |  |  |  | January 2008 |  |  |  | February 2008 |  |  |  | March 2008
[8 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
0001 | Rekonstruction of building into production hall | 2007-10-01 | 2008-03-31 | 0 | 9123.13 | 130 | 5
1 | Zmení práce (Earthworks) | 2007-10-05 | 2007-10-20 | 105698 | 173.89 | 11 | 1.86
2 | Základy a zvláštní zakládání (Foundations) | 2007-10-17 | 2007-10-31 | 245897 | 327.41 | 11 | 3.5
3 | Svislé a kompletní konstrukce (Vertical constructions) | 2007-10-29 | 2007-11-14 | 395877 | 352.35 | 13 | 3.19
4 | Vodorovné konstrukce (Horizontal constructions) | 2007-11-12 | 2007-11-20 | 25693 | 40.4 | 7 | 0.68
5 | Komunikace (Roads) | 2008-01-21 | 2008-02-20 | 132685 | 88.44 | 23 | 0.45
61 | Upravy povrchů vnitřní (Construction of surfaces - internal) | 2007-12-18 | 2008-01-19 | 754821 | 1340.88 | 23 | 6.86
62 | Úpravy povrchů vnější (Construction of surfaces - external) | 2008-02-26 | 2008-03-25 | 799638 | 566.83 | 20 | 3.33
63 | Podlahy a podlahové konstrukce (Floors and floor constructions) | 2008-01-22 | 2008-02-16 | 787451 | 835.73 | 18 | 5.46
64 | Výplně otvorů (Opening panels) | 2007-11-11 | 2007-11-21 | 25400 | 38.57 | 9 | 0.5
8 | Trubní vedení (Pipage, conduction) | 2007-12-10 | 2007-12-24 | 258710 | 203.61 | 11 | 2.18
9 | Ostatní konstrukce, bourání (Other constructions, demolition works) | 2007-10-02 | 2007-10-17 | 130258 | 0 | 12 | 0
94 | Lešení a stavební výtahy (Scaffolding, building lifts) | 2007-10-01 | 2008-03-31 | 165897 | 379.86 | 130 | 0.34
95 | Dokončovací konstrukce (Finishing construcructions) | 2007-11-28 | 2007-12-18 | 3520 | 20.19 | 15 | 0.16
96 | Bourání konstrukcí (Demolition of constructions) | 2007-10-12 | 2007-10-28 | 10320 | 33.84 | 12 | 0.33
97 | Prorážení otvorů (Tapping) | 2007-10-22 | 2007-11-11 | 100025 | 674.1 | 15 | 5.29
98 | Demolice (Demolition) | 2007-11-07 | 2007-11-17 | 35698 | 127.69 | 7 | 2.15
99 | Staveništní přesun hmot (Building site material moving) | 2007-10-01 | 2008-03-31 | 199687 | 998.12 | 130 | 0.9
F0862 | Požární zabezpečení = EPS (Fire protection) | 2008-02-25 | 2008-03-16 | 195000 | 0 | 14 | 0
F0863 | Zabezpečovací zařízení (Protection device) | 2008-02-11 | 2008-03-02 | 86900 | 0 | 14 | 0
F1015 | Doplňkové stavby (Additional buildings) | 2008-01-26 | 2008-02-09 | 658921 | 0 | 11 | 0
711 | Izolace proti vodě (Waterproofing) | 2007-11-23 | 2007-12-05 | 423100 | 355.28 | 10 | 4.18
713 | Izolace tepelné (Thermal insulation) | 2007-12-03 | 2007-12-15 | 5698 | 6.01 | 9 | 0.08
722 | Vnitřní vodovod (Internal water tap) | 2007-12-19 | 2008-01-16 | 74100 | 66.48 | 21 | 0.37
766 | Konstrukce truhlářské (Joinery constructions) | 2008-03-06 | 2008-03-23 | 141259 | 21.4 | 12 | 0.21
767 | Konstrukce zámečnické (Locksmith constructions) | 2008-01-26 | 2008-02-11 | 256900 | 107.71 | 13 | 0.97
771 | Podlahy z dlaždic a obklady (Floors from tiles, wall facing) | 2008-02-12 | 2008-03-11 | 540236 | 1264.44 | 20 | 7.44
776 | Podlahy povlakové (Coating floors) | 2008-03-10 | 2008-03-27 | 14236 | 13.35 | 14 | 0.11
777 | Podlahy ze syntetických hmot (Synthetic floors) | 2008-03-03 | 2008-03-13 | 18569 | 49.07 | 9 | 0.64
781 | Obklady keramické (Ceramic facing) | 2008-02-02 | 2008-02-18 | 5498 | 13.78 | 13 | 0.12
783 | Nátěry (Coating) | 2008-03-08 | 2008-03-20 | 25690 | 1.82 | 10 | 0.02
784 | Malby (Paintings) | 2008-03-16 | 2008-03-31 | 85023 | 372.25 | 12 | 3.65
M21 | Elektromontáže (Electro assembly works) | 2007-12-14 | 2008-03-13 | 758900 | 0 | 65 | 0
D96 | Přesuny suti a vybouraných hmot (Shifts of rubble) | 2007-11-20 | 2007-12-18 | 142000 | 649.64 | 21 | 3.64
3 VRN | Přesun stavebních kapacit (moving of construction capacities) | 2007-10-01 | 2008-03-31 | 82540 | 0 | 130 | 0
5 VRN | Zařízení staveniště (building site accesories) | 2007-10-01 | 2008-03-31 | 174120 | 0 | 130 | 0
Cena za týden (Price for a week)
Cena za měsíc (Price for a month)
Cena za čtvrtletí (Price for a quarter)
Cena za rok (Price for a year)

## Financial saving
Financial saving of building
Supplier:
Number | Název (name of activity) | Financial amount | Financial amount | Financial saving
|  | BUDGET | ACCOUNTING
0001 | Rekonstruction of building into production hall
1 | Zmení práce (Earthworks)
2 | Základy a zvláštní zakládání (Foundations)
3 | Svislé a kompletní konstrukce (Vertical constructions)
4 | Vodorovné konstrukce (Horizontal constructions)
5 | Komunikace (Roads)
61 | Upravy povrchů vnitřní (Construction of surfaces - internal)
62 | Úpravy povrchů vnější (Construction of surfaces - external)
63 | Podlahy a podlahové konstrukce (Floors and floor constructions)
64 | Výplně otvorů (Opening panels)
8 | Trubní vedení (Pipage, conduction)
9 | Ostatní konstrukce, bourání (Other constructions, demolition works)
94 | Lešení a stavební výtahy (Scaffolding, building lifts)
95 | Dokončovací konstrukce (Finishing construcructions)
96 | Bourání konstrukcí (Demolition of constructions)
97 | Prorážení otvorů (Tapping)
98 | Demolice (Demolition)
99 | Staveništní přesun hmot (Building site material moving)
F0862 | Požární zabezpečení = EPS (Fire protection)
F0863 | Zabezpečovací zařízení (Protection device)
F1015 | Doplňkové stavby (Additional buildings)
711 | Izolace proti vodě (Waterproofing)
713 | Izolace tepelné (Thermal insulation)
722 | Vnitřní vodovod (Internal water tap)
766 | Konstrukce truhlářské (Joinery constructions)
767 | Konstrukce zámečnické (Locksmith constructions)
771 | Podlahy z dlaždic a obklady (Floors from tiles, wall facing)
776 | Podlahy povlakové (Coating floors)
777 | Podlahy ze syntetických hmot (Synthetic floors)
781 | Obklady keramické (Ceramic facing)
783 | Nátěry (Coating)
784 | Malby (Paintings)
M21 | Elektromontáže (Electro assembly works)
D96 | Přesuny suti a vybouraných hmot (Shifts of rubble)
3 VRN | Přesun stavebních kapacit (moving of construction capacities)
5 VRN | Zařízení staveniště (building site accesories)
TOTALLY

## 1st variant of payments
Variant payments
Financial cash flows - monthly maturity of invoice
Returns and costs
Year | Month | Week | Supplier invoices | Investor invoices | Creation of economic result
2007 | October | 1.
2.
3.
4.
| November | 1.
2.
3.
4.
| December | 1.
2.
3.
4.
2008 | January | 1.
2.
3.
4.
| February | 1.
2.
3.
4.
| March | 1.
2.
3.
4.
Cash flows
Year | Month | Week | Payment of supplier invoices | Payment of investor invoices | Creation of net cash flow
2007 | October | 1.
2.
3.
4.
| November | 1.
2.
3.
4.
| Decemnber | 1.
2.
3.
4.
2008 | January | 1.
2.
3.
4.
| February | 1.
2.
3.
4.
| March | 1.
2.
3.
4.
| April | 1.
2.
3.
4.

## 2nd variant of payments
Variant payments
Financial cash flows - monthly maturity of invoice, invoices issued after finnishing of particular phases
Returns and costs
Year | Month | Week | Supplier invoices | Investor invoices | Creation of economic result
2007 | October | 1.
2.
3.
4.
| November | 1.
2.
3.
4.
| December | 1.
2.
3.
4.
2008 | January | 1.
2.
3.
4.
| February | 1.
2.
3.
4.
| March | 1.
2.
3.
4.
Cash flows
Year | Month | Week | Payment of supplier invoices | Payment of investor invoices | Creation of net cash flow
2007 | October | 1.
2.
3.
4.
| November | 1.
2.
3.
4.
| Decemnber | 1.
2.
3.
4.
2008 | January | 1.
2.
3.
4.
| February | 1.
2.
3.
4.
| March | 1.
2.
3.
4.
| April | 1.
2.
3.
4.