## Earthworks
INFORMATIVE | [6 empty] | COMPUTATIONAL |  |  |  |  | GRAPHIC
Building | Phase/ Operation | no. | Name | Specific Units | No. of SU | Standard hours per specific unit | Standard hours in sum | Shift working (hours) | Operating (working) stress | No. of workers | Total time | Number of Working Days
|  |  |  | [SU] |  | [Sh/SU] |  |  | [%]
[12 empty] | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Constr. Object 01 | Earthworks | 1 | Site Inspection and Preparation | set | x | 2 | = 6 x 7 | 8 hours | 1 (100%) | 5 | = 8 / 9 / 11 (for workers)
|  | 2 | Construction Site Levelling (roughly) | complete |  | 3 |  |  | x |  | = 8 / 9 (for machinery)
|  | 3 | Erection of a Fence | m2 |  | 0.061 |  |  | 1
|  | 4 | Tree Removal | piece |  | viz. table
|  | 5 | Removal of Shrubs | m2 | 100 | 0.17
|  | 6 | Burning of Gathered Vegetation | set |  | 5
|  | 7 | Topsoil Removal | m3 |  | 0,014 - 0,02*
|  | 8 | Levelling of the Building | set |  | 3 - 5
|  | 9 | Bench Marks Assembly | piece |  | 0.48
|  | 10 | Levelling of the Foundation Pit | 100 m |  | 7.67
|  | 11 | Excavation of Foundation Pit | m3 |  | 0.0386
|  | 12 | Levelling of theFoundation Trenches | 100 m |  | 7.67
|  | 13 | Excavation of Foundation Trenches | m3 |  | 0.0386
|  | 14 | Manual Final Treatment | m3 |  | 1,94 - 2,7
Trunk removal:
hardwood |  |  | Sh/piece
trunk to Ø30cm |  |  | 0.49
trunk to Ø50cm |  |  | 0.88
trunk to Ø70cm |  |  | 1.42
softwood |  |  | Sh/piece
trunk to Ø30cm |  |  | 0.28
trunk to Ø50cm |  |  | 0.55
trunk to Ø70cm |  |  | 0.88
|  |  |  | SU | Sh/SU
Construction Site Levelling (roughly): |  |  |  | complete | 3